## PRN221_NET1706_BCB
Overall Project
Group Name: | BCB |  | Note : -
Max Mark :
Student Percent (%) | 100%
Teacher Percent (%) | 40%
No | Student ID | Student Name | Class Name | Student Percent | Teacher Percent (%) | Mark | Note
1 | SE171676 | Nguyễn Vĩ Tiến | NET1706 | 27% | 10% | 0
2 | SE171688 | Nguyễn Xuân Đức | NET1706 | 24% | 10% | 0
3 | SE171626 | Trần Vũ Khải | NET1706 | 23% | 10% | 0
4 | SE172756 | Nguyễn Văn Minh | NET1706 | 26% | 10% | 0

## Group Tasks
Task List
No | Task Name | Percent (%) | Student Name | Created At | Updated At | Status | Note
1 | Login | 100% | VanMinh | 2024-06-15 | 2024-06-16 | Done
2 | Logout | 100% | VanMinh | 2024-06-21 | 2024-06-22 | Done
3 | Register | 100% | VanMinh | 2024-06-15 | 2024-06-16 | Done
4 | Forgot password | 100% | VanMinh | 2024-06-19 | 2024-06-20 | Done
5 | View student profile | 100% | VanMinh | 2024-06-21 | 2024-06-22 | Done
6 | Edit student profile | 100% | VanMinh | 2024-06-21 | 2024-06-22 | Done
7 | Rating | 100% | VanMinh | 2024-07-06 | 2024-07-07 | Done
8 | View incomplete/ pending tutors | 100% | VanMinh | 2024-06-24 | 2024-06-25 | Done
9 | Approve/ deny pending tutor register account | 100% | VanMinh | 2024-06-24 | 2024-06-25 | Done
10 | Admin Dash board | 100% | VanMinh | 2024-07-10 | 2024-07-11 | Done
11 | Done and rate booking | 100% | VanMinh | 6/7/0204 | 6/7/0204 | Done
12 | Payment | 10% | VanMinh | 6/7/0204 |  | Proccess
13 | View Student Complete | 100% | ViTien | 2024-07-06 | 2024-07-07 | Done
14 | Report | 100% | ViTien | 2024-07-06 | 2024-07-07 | Done
15 | Cancel tutor | 100% | ViTien | 2024-07-07 | 2024-07-08 | Done
16 | View student learning | 100% | ViTien | 2024-06-15 | 2024-06-16 | Done
17 | View tutor learing | 100% | ViTien | 2024-06-19 | 2024-06-20 | Done
18 | Add layout | 100% | ViTien | 2024-06-15 | 2024-06-16 | Done
19 | Manage student rental request | 100% | ViTien | 2024-06-23 | 2024-06-24 | Done
20 | Create tutor profile (Upload image, Upload certificate, Upload self description | 100% | ViTien | 2024-06-28 | 2024-06-29 | Done
21 | View tutor profile | 100% | ViTien | 2024-06-28 | 2024-06-29 | Done
22 | Edit tutor profile | 100% | ViTien | 2024-06-28 | 2024-06-29 | Done
23 | View services | 100% | VuKhai | 2024-06-26 | 2024-06-27 | Done
24 | Rent tutor | 100% | VuKhai | 2024-06-28 | 2024-06-29 | Done
25 | Search tutor | 100% | VuKhai | 2024-06-28 | 2024-06-29 | Done
26 | Search subject | 100% | VuKhai | 2024-06-27 | 2024-06-28 | Done
27 | View detail registered student | 100% | VuKhai | 2024-06-15 | 2024-06-16 | Done
28 | Create service | 100% | VuKhai | 2024-06-19 | 2024-06-20 | Done
29 | Delete service | 100% | VuKhai | 2024-06-19 | 2024-06-20 | Done
30 | Accpet/Denied student booking | 100% | VuKhai | 2024-06-15 | 2024-06-16 | Done
31 | Add layout | 100% | VuKhai | 2024-06-15 | 2024-06-16 | Done
32 | Chat with tutor | 0% | VuKhai |  |  | None
33 | View registered student list (Rented, Renting) | 100% | XuanDuc | 2024-06-15 | 2024-06-16 | Done
34 | Ban user | 100% | XuanDuc | 2024-06-15 | 2024-06-16 | Done
35 | Create account mod | 100% | XuanDuc | 2024-07-02 | 2024-07-03 | Done
36 | Change password mod by admin | 0% | XuanDuc |  |  | None
37 | Get Account | 100% | XuanDuc | 2024-06-20 | 2024-06-21 | Done
38 | Delete Account | 100% | XuanDuc | 2024-06-20 | 2024-06-21 | Done
39 | Active Account | 100% | XuanDuc | 2024-06-20 | 2024-06-21 | Done
40 | View complaint | 100% | XuanDuc | 2024-07-05 | 2024-07-06 | Done
41 | View detail complaint | 100% | XuanDuc | 2024-07-06 | 2024-07-07 | Done
42 | View tutors | 100% | XuanDuc | 2024-06-15 | 2024-06-16 | Done
43 | Suggest tutors (Most Likes, Highest rate, Nearest location) | 50% | XuanDuc |  |  | Proccess
44 | Authencation | 100% | XuanDuc | 2024-07-07 | 2024-07-08 | Done
None
None